## GanttChart_pesquisa
|  | Project | Name - Release 1
|  | Project Start Date | 2025-06-30 |  |  |  |  | Display Week | 1
|  | Project End Date | 2025-11-28 | [6 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13
|  | Project Lead | João | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
SENAI IoT | TASK | ISSUE JIRA | LEAD | PREDECESSOR | ISSUE - MIG/UNIF | START WEEK | WEEKS | END WEEK | % DONE | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22
1 | Revisão do problema |  |  |  |  | 1 | 4 | 4 | 0%
0.1 | Apresentar proposta de estrutura |  | João |  |  | 1 | 2 | 2 | 0%
0.1 | Elaborar escopo e cronograma |  | Maria |  |  | 1 | 2 | 2 | 0%
0.1 | Definir estrutura e local de armazenamento das informações |  | João, Maria, Cleber |  | WTPD-3589 | 2 | 1 | 2 | 0%
0.1 | Definir estratégia de cálculos |  | João, Maria, Cleber |  |  | 2 | 1 | 2 | 0%
0.1 | Definir estrutura para armazenamento da saída do diagnóstico (atributo,file,datatable, etc.) |  | João, Maria, Cleber |  |  | 2 | 1 | 2 | 0%
0.1 | Mapear interseções com migração e unificação |  | João, Maria, Cleber |  |  | 1 | 4 | 4 | 0%
0.1 | Construir modelo |  | João |  |  | 1 | 3 | 3 | 0%
0.1 | Construir modelo básico de planilhas |  | Cleber |  | WTPD-4020 | 1 | 3 | 3 | 0%
0.1 | Construir modelo básico de script |  | Cleber |  | WTPD-4023 | 1 | 3 | 3 | 0%
1 | Desenvolvimentos |  |  |  |  | 4 | 2 | 5 | 0%
0.1 | Pesquisa bibliográfica |  |  |  |  | 4 | 2 | 5 | 0%
0.1 | Pesquisa bibliográfica |  |  |  |  | 4 | 2 | 5 | 0%
0.1 | Escrita de memorial de cálculo |  |  |  |  | 4 | 2 | 5 | 0%
1 | Testes e Documentação |  |  |  |  | 6 | 1 | 6 | 0%
0.1 | Pesquisa bibliográfica |  |  |  |  | 6 | 1 | 6 | 0%
0.1 | Escrita de memorial de cálculo |  |  |  |  | 6 | 1 | 6 | 0%
0.1 | Revisão dos diagnósticos atuais |  |  | 3.2 |  | 6 | 1 | 6 | 0%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet. -Vertex42
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks. -Vertex42
Note on D7: Task Lead Enter the name of the Task Lead in this column. -Vertex42
Note on E7: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor. -Predecessor Tasks
Note on G7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task. -Vertex42
Note on H7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column. -Vertex42
Note on I7: The End Date is calculated based on the Start Date and the Calendar Days columns. -End Date
Note on J7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%). -Vertex42